## ARP4
Portsmouth Water Climate Change Risk Assessment
Version | 4
Version Date | 2024-12-18
Version Owner | Jamie Jones - Strategy and Business Planning Manager
|  |  |  | First Round |  |  | Second Round |  |  | Third Round |  |  |  | Updated for ARP4
Risk management mechanism | Business function | Linked key CCRA3 risk | CCRA3 Risk Name | Risk score (near term) | Risk score (medium term) | Risk score (long term) | Risk score (near term) | Risk score (medium term) | Risk score (long term) | Risk score (near term) | Risk score (medium term) | Risk score (long term) | Risk description | Future actions | Activity 2020-2025 against action plan to mitigate risk | New Data that may change risk | Round 4 Amendment | Risk score (near term) | Risk score (medium term) | Risk score (long term)
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 5 | 20 | 25 | 3 | 6 | 9 | 3 | 6 | 9 | Increased demand for water at peak from permanent population, driven by reduced rainfall and higher temperatures | Continue researching climate drivers of peak demand through WRSE. | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth. | WRMP24 findings on supply/demand gap. | We will have funded smart metering and leakage reduction programmes to reduce demand, so likelihood has been mitigated. | 3 | 6 | 9
WRMP | Water resources | H10 | Risks to health from poor water quality and household supply interruptions | 5 | 20 | 25 | 3 | 6 | 9 | 3 | 6 | 9 | Increased demand from seasonal (tourist) population at peak | Continue researching climate drivers of peak demand through WRSE. Continued engagement with regional planners. Review third party data. Incorporate risk in to future water resources management planning cycles as per regulatory guidelines and implement de | A key objective of the WRSE regional plan is to address the impacts of climate change on demand for water and how much is available. The impact of weather on demand was modelled in 2020, including seasonal factors, minimum and maximum temperatures and rainfall. |  | No change. | 3 | 6 | 9
WRMP and DP | Water resources | I8 | Risks to public water supplies from reduced water availability | 5 | 15 | 20 | 3 | 6 | 9 | 3 | 6 | 9 | Increased occurrence of drought | Business Plan for 2025-2030 includes plans to assess the impacts of climate change on our drought plan. The next drought plan will be published in 2027 and will incorporate the findings of WRMP24 and consider climate change. WRMP29 may change Temporary Use Bans level of service from 1-in-20 to 1-in-10. | WRMP24 assesses the impact of climate change on supply, demand and headroom. WRMP24 plans for an average normal year, a dry year, and a critical period (e.g., summer peak demands) in a dry year. WRMP24 included options to reduce the level of service from a 1-in-500 to a 1-in-200 level of service from a supply side. Last drought plan was finalised in 2022 and proved effective during 2022 drought period. | WRMP24 findings on supply/demand gap. Success of drought plan during 2022 droughts. | We have plans in place to mitigate risk, through funded actions set out in WRMP24. | 3 | 6 | 9
WRMP | Water resources | H10 | Risks to health from water quality and household water supply (b) water quantity | 3 | 9 | 15 | 2 | 6 | 9 | 2 | 3 | 6 | Increased demand from net inward migration of retirement population | Continue researching climate drivers of peak demand through WRSE. Continued engagement with regional planners. Review third party data. Incorporate risk in to future water resources management planning cycles as per regulatory guidelines and implement demand management and/or supply schemes as required | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. |  | No change. | 2 | 3 | 6
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 9 | 9 | 12 | 2 | 6 | 9 | 2 | 6 | 9 | Increased risk of breach of environmental flow requirements in water courses, reducing reliability of sources for public water supply | Continued engagement with Environment Agency. | WRSE developed a series of future scenarios under differing levels of environmental protection. The outcome, a range of potential abstraction licence reductions and resulting reduced deployable output, were embedded into WRMP24. | WRMP24 findings on potential abstraction license reductions and subsequent reduced deployable output. | We have funded plans in place for the short and medium term to mitigate risk, however increased risk in long-term as currently only an adaptative scenario in LTDS. | 3 | 6 | 12
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 3 | 9 | 12 | 2 | 6 | 9 | 2 | 6 | 6 | Increased summer abstraction by other (existing) catchment users due to reduced rainfall | Continue to work with other companies through WRSE. Engage with the Environment Agency and Regional Planners. | Worked alongside neighbouring water companies towards WRSE Regional Plan. Continued works on the Havant Thicket Reservoir to supply water to our customers and free up supplies elsewhere to share with Southern Water. |  | No change. | 2 | 6 | 6
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 3 | 9 | 12 | 2 | 6 | 9 | 2 | 6 | 9 | Increase in agriculture leads to increase in abstraction by other catchment users | Continued engagement with Environment Agency and regional planners. Make use of third party data. Share knowledge through WRSE and Water UK. | Engagement with National Farmers Union (NFU) and the Horticultural Traders Association as part of WRSE. WRMP24 has considered possible further development of Havant Thicket to allow for recycled water from Southern Water’s Budds Farm wastewater treatment works to be used as a source of raw water for the reservoir. |  | No change. | 2 | 6 | 9
WRMP | Water resources | N10 | Risks to aquifers and agricultural land from sea level rise, saltwater intrusion | 4 | 4 | 8 | 2 | 4 | 4 | 2 | 4 | 4 | Saline intrusion of borehole sources | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29 and to better understand the risks of saline intrusion into our groundwater aquifers. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | Likelihood is already low but reduced in medium term based on Arcadis findings. | 2 | 2 | 4
WRMP | Water resources | N10 | Risks to aquifers and agricultural land from sea level rise, saltwater intrusion | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Rising salinity at River Itchen intake | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29 and to better understand the risks of saline intrusion into our groundwater aquifers. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. However the River Itchen IWP was found to be at moderate risk of tidal flooding. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. Investigation ongoing. Look to change if needed in Round 5. | 5 | 5 | 5
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Reduced aquifer recharge during summer months causes reduced summer source yield | Commitments in the next business planning period to assess the effects of our current abstractions and implement mitigation to protect and enhance the aquatic environment. This includes seasonal characteristics of aquifers as a result of climate change. | WRMP24 models supply under various scenarios and considers seasonal variation. Measures to reduce reliance on chalk aquifers include the construction of Havant Thicket. |  | No change. | 5 | 5 | 5
WRMP | Water resources | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 2 | Population migration away from flood risk impacts regional supply-demand balance | Continue researching climate drivers of peak demand through WRSE. Continued engagement with regional planners. Review third party data. Incorporate risk in to future water resources management planning cycles as per regulatory guidelines and implement demand management and/or supply schemes as required | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. |  | No change. | 2 | 2 | 2
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 2 | 4 | 4 | 2 | 4 | 4 | 2 | 4 | 4 | Increased evapotranspiration reducing aquifer recharge | Commitments in the next business planning period to assess the effects of our current abstractions and implement mitigation to protect and enhance the aquatic environment. This includes seasonal characteristics of aquifers as a result of climate change. | WRMP24 models supply under various scenarios and considers seasonal variation. Measures to reduce reliance on chalk aquifers include the construction of Havant Thicket. |  | No change. | 2 | 4 | 4
WRMP | Water resources | I3 | Risks to infrastructure services from coastal flooding and erosion | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Water resources asset loss from coastal change | Continued engagement with regional planners. Ongoing monitoring. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. Arcadis' Climate Change Risk Assessment considered coastal hazards including tidal flooding and saline intrusion from sea level rise and storm surge. |  | No change. | 2 | 2 | 4
WRMP | Water resources | N10 | Risks to aquifers and agricultural land from sea level rise, saltwater intrusion | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Saline intrusion from lower groundwater / increased abstraction | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29 and to better understand the risks of saline intrusion into our groundwater aquifers. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 4 | 4 | 4
WRMP | Water resources | I8 | Risks to public water supplies from reduced water availability | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Reduced aquifer recharge during summer months leads to reduced source yield in October | Commitments in the next business planning period to assess the effects of our current abstractions and implement mitigation to protect and enhance the aquatic environment. This includes seasonal characteristics of aquifers as a result of climate change. | WRMP24 models supply under various scenarios and considers seasonal variation. Measures to reduce reliance on chalk aquifers include the construction of Havant Thicket. |  | No change. | 3 | 3 | 3
WRMP | Water resources | N10 | Risks to aquifers and agricultural land from sea level rise, saltwater intrusion | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Saline intrusion of Havant and Bedhampton Springs source | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29 and to better understand the risks of saline intrusion into our groundwater aquifers. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 2 | 2 | 2
WRMP | Water resources | I3 | Risks to infrastructure services from coastal flooding and erosion | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Population migration away from coastal change impacting regional supply-demand balance | Continue researching climate drivers of peak demand through WRSE. Continued engagement with regional planners. Review third party data. Incorporate risk in to future water resources management planning cycles as per regulatory guidelines and implement demand management and/or supply schemes as required | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. |  | No change. | 2 | 2 | 2
WRMP | Water resources | N4 | Risk to soils from changing climatic conditions, including seasonal aridity and wetness. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Increased soil compaction reduces aquifer recharge | Commitments in the next business planning period to assess the effects of our current abstractions and implement mitigation to protect and enhance the aquatic environment. This includes seasonal characteristics of aquifers as a result of climate change. | WRMP24 models supply under various scenarios and considers seasonal variation. Measures to reduce reliance on chalk aquifers include the construction of Havant Thicket. |  | No change. | 1 | 1 | 1
WRMP | Water resources | N11 | Risks to freshwater species and habitats from changing climatic conditions and extreme events, including higher water temperatures, flooding, water scarcity and phenological shifts. | [6 empty] | 12 | 9 | 9 | Future WINEP reductions exacerbate impacts of flow reductions due to climate change | Between 2025 and 2035, we’ll be carrying out WINEP environmental assessments for all the river catchments – including those for the Itchen, Ems, Meon and Lavant. | Seven of 18 WINEP schemes have been completed. Progress is positive including for those being jointly undertaken with Southern Water and South East Water. |  | No change. | 12 | 9 | 9
Capital Planning | Potable transport | I7 | Risks to subterranean and surface infrastructure from subsidence | 4 | 12 | 16 | 3 | 6 | 9 | 3 | 6 | 9 | Accelerated asset deterioration of cast iron water mains from more extreme wetting and drying cycles and earth movement | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 3 | 6 | 9
Capital Planning | Potable transport | I7 | Risks to subterranean and surface infrastructure from subsidence | 4 | 8 | 12 | 4 | 8 | 12 | 4 | 8 | 12 | Accelerated asset deterioration of ductile iron, fibre reinforced concrete, PVC and steel water mains from more extreme wetting and drying cycles and earth movement | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 4 | 8 | 12
Capital Planning | Abstraction | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Accelerated abstraction asset deterioration (from wetting and drying cycles) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 2 | 2 | 4
Capital Planning | Abstraction | I3 | Risks to infrastructure services from coastal flooding and erosion | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Abstraction asset loss or outage from coastal change | Continued engagement with regional planners. Ongoing monitoring. Continued use of CopperLeaf tool and consideration of climate risks. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 2 | 2 | 4
Capital Planning | Raw transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Reduced raw water transportation pump (M&E) efficiency | CopperLeaf business support tool requires investment options to consider climate change. | Routine asset performance monitoring. Arcadis Climate Change Risk Assessment included risks associated with reduced efficiency of equipment due to high temperatures. |  | No change. | 2 | 2 | 4
Capital Planning | Potable transport | I7 | Risks to subterranean and surface infrastructure from subsidence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Accelerated asset deterioration of MDPPE and HPPE water mains (wetting and drying cycles; earth movement) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 4 | 4 | 4
Capital Planning | Raw transport | I8 | Risks to public water supplies from reduced water availability | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Raw water boosters asset loss from coastal change | Continued engagement with regional planners. Ongoing monitoring. Continued use of CopperLeaf tool and consideration of climate risks. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 4 | 4 | 4
Capital Planning | Treatment | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | Reduced treatment pump (M&E) efficiency | CopperLeaf business support tool requires investment options to consider climate change. | Routine asset performance monitoring. Arcadis Climate Change Risk Assessment included risks associated with reduced efficiency of equipment due to high temperatures. |  | No change. | 1 | 2 | 3
Capital Planning | Potable storage | I3 | Risks to infrastructure services from coastal flooding and erosion | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Asset loss or outage of service reservoirs from coastal change | Continued engagement with regional planners. Ongoing monitoring. Continued use of CopperLeaf tool and consideration of climate risks. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 3 | 3 | 3
Capital Planning | Potable transport | I3 | Risks to infrastructure services from coastal flooding and erosion | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Population migration away from coastal change (network sizing) | Continued use of CopperLeaf tool and consideration of climate change when developing new or replacing long term assets. | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. Findings of WRMP24 feed into capital planning. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 2 | 2 | 2
Capital Planning | Abstraction | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Reduced abstraction pump (M&E) efficiency | CopperLeaf business support tool requires investment options to consider climate change. | Routine asset performance monitoring. Arcadis Climate Change Risk Assessment included risks associated with reduced efficiency of equipment due to high temperatures. |  | No change. | 2 | 2 | 2
Capital Planning | Abstraction | I8 | Risks to public water supplies from reduced water availability | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | River Itchen intake too high due to low flows | Additional bulk supply to Southern Water from the River Itchen is no longer being considered in WRMP24. WRMP24 includes plans to Reduce the amount of water we supply to Southern Water’s customers in West Sussex and Hampshire from 2040 as their planned new resources come into operation and potentially receive supplies from Southern Water after 2039. | Continued to monitor intake yields. |  | No change. | 2 | 2 | 2
Capital Planning | Raw transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Accelerated asset deterioration of raw water booster assets (wetting and drying cycles) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 2 | 2 | 2
Capital Planning | Treatment | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Accelerated deterioration of treatment assets (wetting and drying cycles) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 2 | 2 | 2
Capital Planning | Potable transport | I3 | Risks to infrastructure services from coastal flooding and erosion | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Potable water mains asset loss due to coastal change | Continued engagement with regional planners. Ongoing monitoring. Continued use of CopperLeaf tool and consideration of climate risks. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 2 | 2 | 2
Capital Planning | Potable transport | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Increased seasonal (tourist) population (network sizing) | Continued use of CopperLeaf tool and consideration of climate change when developing new or replacing long term assets. | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. Findings of WRMP24 feed into capital planning. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 2 | 2 | 2
Capital Planning | Raw transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Accelerated deterioration of raw water and potable storage assets (wetting and drying cycles) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 1 | 1 | 1
Capital Planning | Treatment | I3 | Risks to infrastructure services from coastal flooding and erosion | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Treatment asset loss or outage from coastal change | Continued engagement with regional planners. Ongoing monitoring. Continued use of CopperLeaf tool and consideration of climate risks. | Coastal erosion has been considered in the Strategic Environmental Assessment (SEA) as part of WRMP24. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 1 | 1 | 1
Capital Planning | Potable storage, potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Reduced potable storage and potable transport pump (M&E) efficiency | CopperLeaf business support tool requires investment options to consider climate change. | Routine asset performance monitoring. Arcadis Climate Change Risk Assessment included risks associated with reduced efficiency of equipment due to high temperatures. |  | No change. | 1 | 1 | 1
Capital Planning | Potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Accelerated deterioration of potable transport assets (wetting and drying cycles) | In line with our Business Plan 2025-2030, we will build our expertise to understand the impacts of climate change and use this expertise in our asset deterioration modelling to help us in preventing future deterioration. | We have trialled the CopperLeaf business support tool. This helps with asset management and operates on a risk-based system, incorporating climate change risks. |  | No change. | 1 | 1 | 1
Capital Planning | Potable transport | H10 | Risks to health from poor water quality and household supply interruptions | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Population migration away from flood risk (network sizing) | Continued use of CopperLeaf tool and consideration of climate change when developing new or replacing long term assets. | WRMP24 looks at impacts of climate change on demand and uses WRSE adaptive planning scenarios which account for plausible forecasts of population growth and migration. Findings of WRMP24 feed into capital planning. CopperLeaf business support tool requires investment options to consider climate change impacts. |  | No change. | 1 | 1 | 1
Resilience, Emergency Planning | Abstraction, treatment, raw and potable transport | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 3 | 9 | 12 | 3 | 9 | 12 | 3 | 9 | 12 | Increased flooding to source and treatment works from rivers and groundwater | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | Increase likelihood in short term based on risk assessment findings. Further resilience investigations to inform Round 5 and PR29. | 6 | 9 | 12
Resilience, Emergency Planning | Raw transport, potable transport | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 3 | 6 | 9 | 3 | 6 | 9 | 3 | 6 | 9 | Increased flooding to pumping stations (raw and potable) and valves from rivers and groundwater | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | Increase likelihood in short term based on risk assessment findings. Further resilience investigations to inform Round 5 and PR29. | 6 | 9 | 12
Resilience, Emergency Planning | Potable transport | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 3 | 6 | 9 | 3 | 6 | 9 | 3 | 6 | 9 | Increased regional flooding from rivers and groundwater impedes routine mains repair | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | Increase likelihood in short term based on risk assessment findings. Further resilience investigations to inform Round 5 and PR29. | 6 | 9 | 12
Resilience, Emergency Planning | Treatment | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 4 | 6 | 2 | 4 | 6 | 2 | 4 | 6 | Road melt events impede treatment works access | Continued engagement with regional planners and road network / transport operators. | Arcadis' Climate Change Risk Assessment considered transport disruption due to extreme heat and subsequent impacts on the ability of site workers to travel to site. Have incorporated heat waves and road melt events into Emergency Plans. Severe Weather Plan uses Met Office weather warnings to convene appropriate teams. | Climate change risk assessment - River Itchen and Farlington Water Treatment Works at moderate to significant risk. | Increase likelihood based on risk assessment findings. | 2 | 4 | 6
Resilience, Emergency Planning | Abstraction, raw transport, treatment, potable storage, potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 3 | 3 | 6 | 3 | 3 | 6 | 3 | 3 | 6 | Increased interruptions to telecommunications and telemetry | Ongoing monitoring | Arcadis' Climate Change Risk Assessment considered the impacts of climate change hazards on IT and communications systems. |  | Increased as we have experienced increased interruptions due to higher frequency of storms. Further resilience investigations to inform Round 5 and PR29. | 6 | 6 | 9
Resilience, Emergency Planning | Abstraction, treatment, raw and potable transport | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Increased pluvial flooding to works and pumping stations | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | Increase likelihood in medium term based on risk assessment findings. Further resilience investigations to inform Round 5 and PR29. | 2 | 4 | 4
Resilience, Emergency Planning | Abstraction, raw transport, treatment, potable storage, potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Storm damage to above ground assets (buildings and overhead cables) | Ongoing monitoring | Arcadis' Climate Change Risk Assessment considered damage to buildings and infrastructure from high wind events. |  | No change. | 2 | 2 | 4
Resilience, Emergency Planning | Potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Road melt events impede routine mains repair | No action required. | Arcadis' Climate Change Risk Assessment considered transport disruption due to extreme heat and subsequent impacts on the ability of site workers to travel to site. Have incorporated heat waves and road melt events into Emergency Plans. Severe Weather Plan uses Met Office weather warnings to convene appropriate teams. | Climate change risk assessment - generally very low to moderate risk. | No change. | 2 | 2 | 4
Resilience, Emergency Planning | Potable transport | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Increased regional pluvial flooding impedes routine mains repair | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | Increase likelihood in medium term based on risk assessment findings. Further resilience investigations to inform Round 5 and PR29. | 2 | 4 | 4
Resilience, Emergency Planning | Potable storage | I2 | Risks to infrastructure services from river, surface water and groundwater flooding | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Service reservoir monitoring equipment failure due to flooding | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | No change. Mitigation in place. | 3 | 3 | 3
Resilience, Emergency Planning | Abstraction | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | Road melt events impede abstraction works access | No action required. | Arcadis' Climate Change Risk Assessment considered transport disruption due to extreme heat and subsequent impacts on the ability of site workers to travel to site. Have incorporated heat waves and road melt events into Emergency Plans. Severe Weather Plan uses Met Office weather warnings to convene appropriate teams. | Climate change risk assessment - generally very low to moderate risk. | No change. | 1 | 1 | 2
Resilience, Emergency Planning | Abstraction, raw transport, treatment, potable storage, potable transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | Increased interruptions to electricity supply | Renewable energy is incorporated into the long term strategy. Solutions are also being considered including a battery park to be implemented in 2025-2030 (pending planning permission). Planning permission would allow a 150MW battery and solar panels floating on reservoirs. Proposing to use Ofwat funding to complete detailed site studies to provide options and costs to delivery power resilience and remote start or auto restarting schemes on those sites most vulnerable to the in-combination risks of power and transport network failures. | Arcadis' Climate Change Risk Assessment considered power loss impacts relating to climate change hazards. We are in the process of delivering a generator upgrade and refurbishment programme. |  | Increased as we have experienced increased interruptions due to higher frequency of storms. Further resilience investigations to inform Round 5 and PR29. | 4 | 4 | 6
Resilience, Emergency Planning | Raw transport | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | Road melt events impede raw water boosters access | No action required. | Arcadis' Climate Change Risk Assessment considered transport disruption due to extreme heat and subsequent impacts on the ability of site workers to travel to site. Have incorporated heat waves and road melt events into Emergency Plans. Severe Weather Plan uses Met Office weather warnings to convene appropriate teams. | Climate change risk assessment - generally very low to moderate risk. | No change. | 1 | 1 | 2
DWSP | Raw water quality | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 6 | 12 | 3 | 6 | 12 | 3 | 6 | 12 | Lower river flows cause higher contaminant concentrations | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 3 | 6 | 12
DWSP | Raw water quality | H10 | Risks to health from poor water quality and household supply interruptions | 4 | 8 | 10 | 4 | 8 | 10 | 4 | 8 | 10 | Reduced cloud cover leads to increased biological growth in surface waters | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 4 | 8 | 10
DWSP | Raw water quality | H10 | Risks to health from poor water quality and household supply interruptions | 4 | 6 | 8 | 4 | 6 | 8 | 4 | 6 | 8 | Higher temperatures cause increased biological and bacterial growth in surface waters | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 4 | 6 | 8
DWSP | Raw water quality | H10 | Risks to health from poor water quality and household supply interruptions | 4 | 6 | 6 | 4 | 6 | 6 | 4 | 6 | 6 | Lower river flows cause warmer water and increased biological and bacterial growth in surface waters | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 4 | 6 | 6
DWSP | Treatment | I1 | Risks to infrastructure networks (water, energy, transport, ICT) from cascading failures | 2 | 4 | 6 | 2 | 4 | 6 | 2 | 4 | 6 | Chemical supply chain disruption from regional heatwaves and floods | Using Ofwat funding we are proposing to conduct a study to increase our understanding of the Climate Change risks embedded in our wider supply chain and actions we might take to mitigate such risks. | Arcadis' Climate Change Risk Assessment considered the impacts of climate change hazards on the chemical supply chain, including during heatwaves when additional chlorine supply is required for water treatment. |  | No change. | 2 | 4 | 6
DWSP | Potable transport | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 6 | 2 | 2 | 4 | 2 | 2 | 4 | Saline intrusion of potable water mains (metallic mains) | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 2 | 2 | 4
DWSP | Raw transport (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Saline intrusion of raw water mains (water quality risk) | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 4 | 4 | 4
DWSP | Raw water quality | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 4 | 4 | 4 | 8 | 8 | 4 | 8 | 8 | Increased turbidity events from runoff (river and springs sources) | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 4 | 8 | 8
DWSP | Potable transport and storage (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Accelerated chlorine depletion in treated water (potable storage and transportation) | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 2 | 2 | 4
DWSP | Potable transport (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | Regional flooding from groundwater and rivers causes infiltration of water mains; bacterial contamination risk | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | No change. Mitigation in place. | 2 | 2 | 4
DWSP | Treatment | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Increased bacterial growth in rapid gravity filters | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 3 | 3 | 3
DWSP | Potable storage (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | Saline intrusion of service reservoirs | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29 and to better understand the risks of saline intrusion into our groundwater aquifers. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 1 | 1 | 1
DWSP | Potable storage (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Infiltration of service reservoirs from flooding | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | No change. Mitigation in place. | 3 | 3 | 3
DWSP | Raw storage (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Increased flooding to raw water storage assets from rivers and groundwater; bacterial contamination, asset damage | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | No change. Mitigation in place. | 3 | 3 | 3
DWSP | Treatment | H10 | Risks to health from poor water quality and household supply interruptions | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | Disturbance of flocculant blanket in treatment | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. |  | No change. | 1 | 1 | 2
DWSP | Treatment | H10 | Risks to health from poor water quality and household supply interruptions | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Bacterial growth in rapid gravity filters | Business Plan 2025-2030 includes incorporating water quality findings from climate risk assessments into DWSP. UV Treatment Plant proposed 2025-2030 to mitigate emerging risk of cryptosporidium. | Working with Water UK Water Quality Group to develop a screening process for DWSP risks identified as part of the source to tap assessment. DWSP and Catchment & Environment Team are in the process of incorporating water quality findings into the DWSP. |  | No change. | 2 | 2 | 2
DWSP | Treatment | H10 | Risks to health from poor water quality and household supply interruptions | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Algal growth in rapid gravity filters and clarifiers | Business Plan 2025-2030 includes aims to reduce algal growth in the Portsmouth, Chichester, Langstone Harbours and River Hamble estuary. | Algal growth was considered in Arcadis' Climate Change Risk Assessment. |  | No change. | 1 | 1 | 1
DWSP | Potable transport (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Increased pluvial flooding leads to infiltration of potable water mains; bacterial contamination risk | Proposing to use Ofwat Draft Determination funding to continue flood risk studies to inform the next Long-Term Delivery Strategy (LTDS), provide fully costed engineering solutions, and suggest, within an adaptive planning framework, when implementation is likely to be required. | Arcadis completed a Climate Change Risk Assessment on 93 assets across 51 sites within the Portsmouth Water supply area, with specific emphasis on sea level rise and storm surge, rainfall events and extreme weather events. | Climate change risk assessment - 15 assets at moderate to major risk of fluvial flooding, 37 assets at moderate to major risk of surface water flooding, 6 sites at high risk of groundwater flooding. | No change. Mitigation in place. | 1 | 1 | 1
DWSP | Potable transport (water quality) | H10 | Risks to health from poor water quality and household supply interruptions | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Saline intrusion of potable water mains (non-metallic mains) | A region-wide investigation into saline intrusion will be completed between 2025 and 2030 to inform WRMP29. | A Climate Change Risk Assessment on 93 assets across 51 sites included consideration of saline intrusion. The assessment found that no abstraction assets were likely to be affected. | Findings from Climate Change Risk Assessment completed in 2023. Outputs from saline intrusion study to be completed 2025-2030 may also change risk. | No change. | 3 | 3 | 3